## Estimations
Issue # | Summary of Tasks | Initial Estimate | Coding Effort | Non-coding effort | Estimator | Implementors
13 | Implement Login & UH Email Verification – Create a mock login form restricted to @hawaii.edu emails; redirect user to profile upon successful login; add validation and error handling. | 3 hours | 2.5 hours | 1 hour | Lara | Lara | *Milestone 1 was not tracked as we did not know the assignment at the time
16 | Improve NavBar | 2 hours | 1 | 0.5 | Lara | Lara
7 | Create a page that lets users view and explore many roommate/room postings at once. | 90 minutes | 60 minutes | 30 minutes | Miley | Miley
29 | Update Browse Listings Page | 3 hours | 2 hours | 0 | Miley | Miley
30 | Update User Profile Page | 3 hours | 4 hours | 0 | Miley | miley
2 | Create landing page | 2 days | 2 days |  | Harry | Harry
37 | Create support page | 3 hours
47 | Add Photo upload feature in Create Profile Page | 3 hours | 1 hour | 5 hours | Miley | Miley
36 | match detail page | 4 hrs | 3.5 hrs | 1 hr | Brooke | Brooke
50 | improve detail profile page | 3 hrs | 3.5 hr | 0.5 hr | Brooke | Brooke
81 | Navbar create profile/edit profile protected | 2 hrs | 1 hr | 0.5 hr | Lara | Lara
68 | Message search bar | 4 hr | 2 | 0.5 hr | Lara | Lara
78 | update github.io page | 1 hr | 0 |  | Brooke
80 | format preferences | 1 hr
86 | username login implementation | 3 hr | 1.5 hr | 1 hr | Lara | Lara
85 | Password Security + File Size Requirements | 3 hr | 2 day | 1 hr | Harry | Harry
75 | Update Homepage | 1 hr | 1 hr | 0 | Harry | Harry
37 | Create a support page | 4 hr | 4 hr | 0.5 hr | Harry | Harry
77 | Fix the upload image function | 4 hr | 4 hrs | 8 hours | Miley | Miley
101 | Remove user profile from listings | 1 hr | 1 hr | 0 | Miley | Miley
6 | Compatibility Algorithm Prototype | 1 hr | 1 hr | 0.5 hr | Ethan | Ethan
8 | Database Schema for Profiles | 2 hr | 2 hr | 1 hr | Ethan | Ethan
31 | Create Meeting/Calendar Model and Functions | 4 hr | 3.5 hr | 1 hr | Ethan | Ethan
32 | Implement GroupChat Feature | 3 hr | 3 hr | 1 hr | Ethan | Ethan
83 | Add Fake Users to Database | 2 hr | 2 hr | 0.5 hr | Brooke | Brooke
78 | Update github.io page with feedback | 0.5 hr | 0 hr | 0.25 hr | Brooke | Brooke
110 | Make Fake Users Visible | 1 hr | 1 hr | 0.5 hr | Ethan | Ethan
79 | Implement Compatibility Algorithm | 3 hr | 3 hr | 1.5 hr | Ethan | Ethan
98 | Fix password icons | 0.2 hr | 0.1 hr | 0 hr | Brooke | Brooke

## Summary
Team Member | Software Development Experience (months) | How was coding Effort Tracked | How was non-coding Effort Tracked
Brooke Clifton | 1 year | recording times in notes | recording times in notes
Miley Chun | 4 months | recording times in notes | recording times in notes
Ethan Garcia | 4 months | recording times in notes | recording times in notes
Harrison Gray | 9 months | recording times in notes | recording times in notes
Lara Miyakawa Ho | 8 months | recorded start time and end time | recorded start time and end time